# OmniTrack MVP Development Plan

Version: 1.0
Last Updated: 2025-12-16
Status: Planning → Implementation

## Table of Contents

- Executive Summary

- MVP Scope & Goals

- Architecture Overview

- Team & Repository Setup

- Implementation Phases

- Development Workflow

- Quality Gates

- Timeline & Milestones

- Success Criteria

- Risks & Mitigations

- Post-MVP Roadmap

## Executive Summary

OmniTrack MVP is a location and operational intelligence platform designed to:

- Ingest real-time telemetry from RTLS vendors (Ubisense, Cisco DNA, Aruba, etc.)

- Normalize and track device/asset positions on indoor venue maps

- Raise alerts based on geofences and dwell rules

- Provide a live web interface for monitoring

Target delivery: 4–6 weeks with a 2–3 person engineering team.

Core value proposition:
"For a single venue, show live positions of devices/assets on a web map and raise configurable alerts when they enter zones or dwell too long."

## MVP Scope & Goals

### What's IN Scope

#### Core Functionality

- ✅ Real-time telemetry ingestion from 1–2 RTLS vendors

- ✅ Position normalization to canonical format (x, y, floor, accuracy)

- ✅ Device state tracking (last known position per device)

- ✅ Indoor mapping (load venue floor plans, render spaces/zones)

- ✅ Geofence alerts (trigger when device enters/exits a zone)

- ✅ Simple dwell alerts (trigger when device stays in zone > N seconds)

- ✅ Live web UI showing:

  - Venue map with device positions

  - Real-time position updates via WebSocket

  - Alert feed

#### Technical Capabilities

- ✅ Single tenant support (multi-tenant data model, but 1 tenant in practice)

- ✅ Event-driven microservices architecture

- ✅ Docker-based local development

- ✅ Basic observability (logs, metrics, health checks)

- ✅ REST APIs + WebSocket for real-time updates

### What's OUT of Scope (for MVP)

- ❌ Multi-tenant UI/UX (admin portal, tenant isolation)

- ❌ Routing/pathfinding

- ❌ Heatmaps, analytics, dashboards

- ❌ Mobile SDKs (iOS/Android)

- ❌ Advanced ML/predictive features

- ❌ Auto-discovery of RTLS vendors

- ❌ Tile generation (use static GeoJSON for MVP)

- ❌ Production Kubernetes deployment (docker-compose only)

### Success Metrics

By end of MVP, we should be able to:

- Ingest 100+ telemetry messages/sec from a simulated or real RTLS feed

- Display live device positions on a web map with < 2s latency

- Raise alerts when devices enter pre-configured geofences

- Demo the system end-to-end to stakeholders in a single venue scenario

## Architecture Overview

### High-Level Architecture

┌─────────────────────────────────────────────────────────────────┐

│                         RTLS Vendors                            │

│              (Ubisense, Cisco DNA, Aruba, etc.)                 │

└────────────────────────┬────────────────────────────────────────┘

│ HTTP/Webhook

▼

┌─────────────────────────────────────────────────────────────────┐

│                    Ingestion Service                            │

│              (Receive raw telemetry, publish to NATS)           │

└────────────────────────┬────────────────────────────────────────┘

│ telemetry.raw

▼

┌─────────┐

│  NATS   │ (Event Bus)

└─────────┘

│

┌────────────────┼────────────────┐

│                │                │

▼                ▼                ▼

┌──────────────┐  ┌──────────────┐  ┌──────────────┐

│Normalisation │  │ Rules &      │  │ Device Twin  │

│   Service    │  │ Alerts       │  │   Service    │

└──────┬───────┘  └──────┬───────┘  └──────┬───────┘

│                 │                 │

│ position.       │ alert.          │ device.

│ resolved        │ raised          │ updated

│                 │                 │

└─────────────────┴─────────────────┘

│

▼

┌─────────────┐

│ API Gateway │

│ (REST + WS) │

└──────┬──────┘

│

▼

┌─────────────┐

│  Web App    │

│ (Live Map)  │

└─────────────┘

### MVP Services

| Service | Responsibility | Tech Stack |
| --- | --- | --- |
| Ingestion Service | Receive raw telemetry via HTTP, publish to NATS | Node.js, Express, NATS |
| Normalisation Service | Transform vendor-specific payloads to canonical format | Node.js, NATS |
| Device Twin Service | Track last-known state per device, expose REST API | Node.js, MongoDB/Postgres |
| Mapping Service | Store venue geometry, serve map data | Node.js, PostGIS |
| Rules & Alerts Service | Evaluate geofence/dwell rules, raise alerts | Go/Node.js, NATS, MongoDB |
| API Gateway | Single entry point, REST + WebSocket | Node.js, Express, Socket.io |
| Web App | Live map UI with device tracking and alerts | React, Leaflet/Mapbox GL |

### Infrastructure (Local Dev)

- NATS – Event bus

- PostgreSQL + PostGIS – Venue geometry, spatial queries

- MongoDB – Device twins, alerts, content

- Redis (optional) – Caching, session store

- Prometheus + Grafana (optional) – Metrics and dashboards

## Team & Repository Setup

### Recommended Team Structure

For a 4–6 week MVP:

- 2–3 Backend Engineers (Node.js/Go, microservices, NATS, databases)

- 1 Frontend Engineer (React, WebSocket, mapping libraries)

- 0.5 DevOps/Platform (Docker, CI/CD, observability)

### Repository Structure

Monorepo (recommended for MVP):

omnitrack/

├── services/

│   ├── ingestion-service/

│   ├── normalisation-service/

│   ├── device-twin-service/

│   ├── mapping-service/

│   ├── rules-alerts-service/

│   └── api-gateway/

├── web/

│   └── web-app/

├── infra/

│   ├── docker-compose.yml

│   ├── docker-compose.dev.yml

│   └── k8s/ (future)

├── docs/

│   ├── architecture/

│   │   ├── overview.md

│   │   ├── data-flows.md

│   │   └── service-specs/

│   ├── api/

│   │   └── openapi.yaml

│   └── MVP_PLAN.md (this file)

├── scripts/

│   ├── seed-venue.sh

│   ├── simulate-telemetry.js

│   └── init-db.sql

├── .github/

│   └── workflows/

│       └── ci.yml

├── package.json (root workspace config)

├── .gitignore

└── README.md

### Tooling & Standards

- Language: TypeScript (Node.js services), Go (optional for Rules service)

- Linting: ESLint + Prettier

- Testing: Jest (unit), Supertest (integration)

- Commit hooks: Husky + lint-staged

- Versioning: Semantic versioning (semver)

- Documentation: Markdown in docs/, inline JSDoc/TSDoc

## Implementation Phases

### Phase 0: Foundations (Week 1)

Goal: Set up repo, infra, and coding standards.

#### Tasks

- Initialize monorepo with workspace structure

- Add shared tooling: ESLint, Prettier, Husky, lint-staged

- Create infra/docker-compose.yml with:

  - NATS

  - PostgreSQL + PostGIS

  - MongoDB

  - Redis (optional)

- Add Makefile or npm scripts:

  - make up / npm run dev:stack – start infra

  - make down – stop infra

  - make logs – tail logs

- Set up CI pipeline (GitHub Actions / GitLab CI):

  - Jobs: lint, test, build

  - Run on every PR, block merge on failure

- Write initial architecture docs:

  - docs/architecture/overview.md

  - docs/architecture/data-flows.md

- Integrate Ingestion Service (already implemented) into monorepo

- Verify Ingestion Service builds and runs via Docker

#### Deliverables

✅ Dev environment is one command away
✅ CI is green
✅ At least one service (Ingestion) runs end-to-end

### Phase 1: Core Data Flow (Weeks 2–3)

Goal: End-to-end path from RTLS telemetry → normalized positions → device twin.

#### Tasks

Normalisation Service

- Create service skeleton (normalisation-service/)

- Connect to NATS, subscribe to telemetry.raw

- Implement vendor adapters:

  - adapters/ubisense.ts

  - adapters/generic.ts

- Transform to canonical NormalizedTelemetry:

- {

- tenantId: string;

- deviceId: string;

- timestamp: string; // ISO 8601

- x: number;

- y: number;

- z?: number;

- floorId: string;

- accuracy?: number;

- metadata?: Record<string, any>;

- }

- Publish to position.resolved

- Add logging, metrics, error handling

- Write unit tests for adapters

Device Twin Service

- Create service skeleton (device-twin-service/)

- Subscribe to position.resolved

- Store latest position per device in MongoDB/Postgres:

- {

- tenantId: string;

- deviceId: string;

- lastPosition: {

- x, y, z, floorId, accuracy, timestamp

- };

- metadata: Record<string, any>;

- updatedAt: Date;

- }

- Expose REST API:

  - GET /devices/{id} – get device state

  - GET /devices?tenantId={id} – list all devices for tenant

- Add health check, metrics

- Write integration tests

Testing & Validation

- Create scripts/simulate-telemetry.js to POST fake telemetry

- End-to-end test:

  - POST telemetry → Ingestion → NATS → Normalisation → Device Twin

  - Verify device state via GET /devices/{id}

#### Deliverables

✅ Telemetry flows from Ingestion → Normalisation → Device Twin
✅ REST API returns last-known device positions
✅ All services have logs, metrics, and tests

### Phase 2: Mapping, Rules, and UI (Weeks 3–4)

Goal: Make OmniTrack visible and useful for a single pilot venue.

#### Tasks

Mapping Service

- Create service skeleton (mapping-service/)

- Define PostGIS schema:

  - venues (id, name, tenant_id)

  - floors (id, venue_id, level, geometry)

  - spaces (id, floor_id, name, type, geometry)

- Create seed script: scripts/seed-venue.sh

  - Load sample venue with 1–2 floors

  - Define 2–3 geofence zones

- Expose REST API:

  - GET /venues/{id} – venue metadata

  - GET /venues/{id}/floors – list floors

  - GET /venues/{id}/map – GeoJSON of spaces/zones

- Add spatial query helpers (point-in-polygon)

Rules & Alerts Service

- Create service skeleton (rules-alerts-service/)

- Define rule schema (MongoDB):

- {

- ruleId: string;

- tenantId: string;

- type: 'geofence' | 'dwell';

- config: {

- zoneId?: string;

- polygon?: GeoJSON;

- dwellSeconds?: number;

- };

- actions: ['alert', 'webhook'];

- }

- Subscribe to position.resolved

- Implement geofence evaluator:

  - Check if device position is inside any geofence polygon

  - Raise alert.raised event if condition met

- Implement simple dwell evaluator (in-memory state):

  - Track device entry time per zone

  - Raise alert if dwell > threshold

- Persist alerts to MongoDB

- Expose REST API:

  - GET /alerts?tenantId={id}&since={timestamp}

  - GET /rules (list rules)

  - POST /rules (create rule)

API Gateway

- Create service skeleton (api-gateway/)

- Implement REST proxy:

  - GET /api/venues/{id}/map → Mapping Service

  - GET /api/devices/{id} → Device Twin Service

  - GET /api/alerts → Rules & Alerts Service

- Add authentication middleware (API key or JWT)

- Implement WebSocket/SSE handler:

  - Subscribe to position.resolved and alert.raised

  - Push updates to connected clients

- Add rate limiting, CORS, security headers

Web App

- Create React app (web-app/)

- Integrate mapping library (Leaflet or Mapbox GL JS)

- Implement features:

  - Load venue map (GeoJSON from API Gateway)

  - Render device markers (from Device Twin API)

  - Connect to WebSocket for live position updates

  - Display alert feed (right-hand panel)

  - Simple search/filter for devices

- Add basic styling (Tailwind CSS or Material-UI)

Integration & Testing

- End-to-end test:

  - Seed venue + geofence

  - Simulate telemetry for devices moving through zones

  - Verify alerts appear in Web App

- Load test: 100 messages/sec for 5 minutes

#### Deliverables

✅ Live web map showing device positions
✅ Real-time updates via WebSocket
✅ Geofence alerts triggered and displayed
✅ End-to-end demo ready for stakeholders

### Phase 3: Stabilization & Hardening (Weeks 5–6, optional)

Goal: Production-readiness improvements.

#### Tasks

- Add second vendor adapter (e.g., Cisco DNA Spaces)

- Implement dwell rule logic (beyond simple geofence)

- Add comprehensive error handling and retries

- Set up Prometheus + Grafana dashboards:

  - Telemetry throughput

  - Service latencies

  - Alert counts

- Write deployment guide (docs/deployment.md)

- Security audit:

  - Secrets management (env vars, not hardcoded)

  - Input validation on all APIs

  - Rate limiting tuned

- Performance tuning:

  - Database indexing

  - NATS message batching

  - WebSocket connection pooling

#### Deliverables

✅ Multi-vendor support demonstrated
✅ Observability dashboards live
✅ Deployment guide complete
✅ Security checklist passed

## Development Workflow

### Branching Strategy

- main – Always deployable, protected branch

- develop (optional) – Staging/QA branch

- Feature branches – One per task/story:

  - feature/normalisation-ubisense-adapter

  - feature/webapp-live-map

  - fix/ingestion-rate-limit-bug

### Pull Request Process

- Create feature branch from main (or develop)

- Implement feature with tests

- Open PR with description:

  - What changed

  - How to test

  - Screenshots (if UI)

- CI checks must pass:

  - Lint

  - Tests

  - Build

- At least 1 approval required

- Squash and merge to main

### Commit Conventions

Use Conventional Commits:

feat(ingestion): add rate limiting middleware

fix(normalisation): handle missing timestamp field

docs(architecture): update data flow diagram

test(device-twin): add integration tests for REST API

### Code Review Guidelines

- Small PRs: Aim for < 500 LOC net diff

- Focus areas:

  - Correctness (logic, edge cases)

  - Testability (unit tests included?)

  - Observability (logs, metrics added?)

  - Security (input validation, auth checks)

- Response time: Review within 24 hours

## Quality Gates

### Testing Requirements

Unit Tests

- All business logic (adapters, rules engine, validators)

- Target: > 70% code coverage

Integration Tests

- API endpoints (Supertest)

- NATS pub/sub flows

- Database queries

End-to-End Tests

- Smoke test: POST telemetry → verify device state

- Alert test: Simulate device entering geofence → verify alert raised

Load Tests (optional for MVP)

- 100 messages/sec sustained for 5 minutes

- Measure: latency p50, p95, p99

### Observability Requirements

Logging

- Structured JSON logs (Winston)

- Log levels: error, warn, info, debug

- Correlation IDs for request tracing

Metrics

- Prometheus metrics for all services:

  - http_requests_total

  - http_request_duration_seconds

  - telemetry_received_total

  - telemetry_errors_total

  - alerts_raised_total

- Expose /metrics endpoint on each service

Health Checks

- /health endpoint on each service

- Check dependencies (NATS, DB connections)

Tracing (optional for MVP)

- OpenTelemetry instrumentation

- Jaeger for distributed tracing

### Security Requirements

- All external APIs require authentication (API key or JWT)

- Input validation on all endpoints (Joi schemas)

- Rate limiting on public endpoints

- Secrets stored in .env, not committed to git

- CORS configured for Web App origin only

- Helmet.js for security headers

## Timeline & Milestones

### 4-Week Timeline (Aggressive)

| Week | Phase |  | Key Deliverables |
| --- | --- | --- | --- |
| Week 1 |  | Phase 0: Foundations | Repo setup, infra running, CI green, Ingestion Service integrated |
| Week 2 |  | Phase 1: Core Data Flow | Normalisation + Device Twin services live, end-to-end telemetry flow working |
| Week 3 |  | Phase 2: Mapping & Rules | Mapping + Rules services live, API Gateway with WebSocket |
| Week 4 |  | Phase 2: UI & Demo | Web App complete, end-to-end demo ready |

### 6-Week Timeline (Recommended)

| Week | Phase | Key Deliverables |
| --- | --- | --- |
| Week 1 | Phase 0: Foundations | Repo setup, infra running, CI green, Ingestion Service integrated |
| Week 2 | Phase 1: Core Data Flow (Part 1) | Normalisation Service complete with 1 vendor adapter |
| Week 3 | Phase 1: Core Data Flow (Part 2) | Device Twin Service complete, end-to-end tests passing |
| Week 4 | Phase 2: Mapping & Rules | Mapping + Rules services live, seed scripts working |
| Week 5 | Phase 2: API & UI | API Gateway + Web App complete, live map working |
| Week 6 | Phase 3: Stabilization | Second vendor adapter, observability dashboards, demo polish |

### Key Milestones

- M1 (End of Week 1): Infrastructure ready, first service running

- M2 (End of Week 3): Core data flow complete (telemetry → device twin)

- M3 (End of Week 5): Full MVP feature-complete

- M4 (End of Week 6): Demo-ready, stakeholder presentation

## Success Criteria

The MVP is considered successful if:

- ✅ Functional:

  - Can ingest telemetry from at least 1 RTLS vendor

  - Displays live device positions on a web map

  - Raises alerts when devices enter geofences

  - All core services running and communicating via NATS

- ✅ Performance:

  - Handles 100+ messages/sec with < 2s end-to-end latency

  - Web UI updates in real-time (< 1s delay)

- ✅ Quality:

  - All services have unit tests (> 70% coverage)

  - CI pipeline green on main

  - No critical security vulnerabilities

- ✅ Demonstrable:

  - Can run full demo in < 5 minutes

  - Stakeholders can see live tracking and alerts

  - Documentation exists for setup and usage

## Risks & Mitigations

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| RTLS vendor integration complexity | High | Medium | Start with generic adapter, add vendor-specific later |
| WebSocket scaling issues | Medium | Low | Use Socket.io with Redis adapter if needed |
| PostGIS spatial query performance | Medium | Low | Add spatial indexes, test with realistic data volumes |
| Scope creep | High | High | Strict adherence to MVP scope, defer non-essential features |
| Team availability | High | Medium | Front-load critical path items, maintain clear backlog |
| NATS message ordering | Medium | Low | Use NATS JetStream if ordering is critical (defer to post-MVP) |

## Post-MVP Roadmap

After MVP is delivered, prioritize:

### Phase 4: Multi-Tenant & Admin (Months 2–3)

- Tenant management UI

- User authentication and RBAC

- Admin portal for venue/geofence configuration

- Tenant isolation and data segregation

### Phase 5: Advanced Features (Months 3–6)

- Routing and pathfinding

- Heatmaps and analytics

- Historical playback

- Custom dashboards

- Mobile SDKs (iOS/Android)

### Phase 6: Production Deployment (Months 4–6)

- Kubernetes deployment (Helm charts)

- Auto-scaling and load balancing

- Multi-region support

- Disaster recovery and backups

- Production monitoring and alerting

### Phase 7: Integrations & Ecosystem (Months 6+)

- Third-party integrations (Slack, Teams, webhooks)

- Public API and developer portal

- Marketplace for plugins/extensions

- ML-based predictive analytics

## Appendix

### Useful Commands

# Start local infrastructure

make up

# Stop infrastructure

make down

# View logs

make logs

# Run tests

npm test

# Lint code

npm run lint

# Build all services

npm run build

# Seed demo venue

npm run seed:venue

# Simulate telemetry

npm run simulate:telemetry

### Key Documentation

- Architecture Overview

- Data Flows

- API Reference

- Deployment Guide

- Contributing Guide

### Contact & Support

- Project Lead: [Name]

- Tech Lead: [Name]

- Slack Channel: #omnitrack-dev

- Issue Tracker: GitHub Issues

Next Steps:

- Review and approve this MVP plan

- Set up repository and infrastructure (Phase 0)

- Kick off Phase 1 implementation

- Schedule weekly sync meetings

- Set up stakeholder demo for end of Week 4/6

This is a living document. Update as the project evolves.